## MasterList2013
Student Services Priorities: 2013 and Beyond
Green = Current; Pink = Future; Yellow = complete; Blue = Removed |  |  |  | Possible Impacted Areas |  |  | Strategic Plan Connection
Category | Project | Status | R1 (lead) | ITS | Instruction | Others | Instit. Sustain. | Transfer | Workforce | Basic Skills | Lifelong Learning | Description | Notes | Date Updated
Adv/Bonus | Student Services indicator report | Current | Chris | ü |  | IE | ü | ü | ü | ü |  | Working with IE, develop a regular process to report on the GPA, retention, progression, and completion rates of student who participate in activities sponsored by Student Services. | Report has been created. Chris to circle back with Chris E. Still working through details of identifying MCA students in a way that allows for automated reporting from IE. | CM 1/14/15
Adv/Bonus | Auto Awarding degrees | Current | Courtney | ü | ü |  | ü | ü | ü | ü |  | Research indicates that automatically awarding certificates or degrees without having the student apply increases an institution’s completion rates. With the advent of career pathways and short-term certificates, institutions have recently shifted the practice of automatically awarding from the student’s “end” certificate or degree to automatically awarding shorter-term certificates as students progress to their end academic goal. Will involve developing criteria and process by which program directors can make substitutions or waivers for CTE certificates or degrees | Phase I is complete. Phase II (TBD what is in phase II) waiting on PAT review and president approval. | AM 1/14/15
Sanity | Transfer articulations: workflow | Current | Courtney |  |  |  |  | ü | ü | ü |  | Review and redesign where appropriate workflow associated with transfer course articulation and certificate or degree awarding process to create greater efficiencies and increase response time. Includes assigning responsibilities to various staff involved with process, reviewing baseline Banner processes and automating processes where possible. | All identified data clean-up activities completed. Meeting next week to identify next steps if any. Does this mean that theservice level agreement with CAP Center will change based on speedier workflow? | SB 1/14/15
Mandatory | Campus FERPA Training | Current | Courtney | ü |  | HR |  | ü | ü | ü | ü | Determine a means of delivering FERPA training to all faculty and staff on a regular basis; note: will need to work with Wesley Dimond re: email security and considerations (already has process set up for HR). | Getting a quote from "safe-campus" on modifying program to meet our needs. Drafting confidentiality language. Still working with this group. No change since last update. | AM 1/14/15
Adv/Bonus | Academic Warning (forms updating) | Current | Courtney |  |  | CAP |  | ü | ü | ü |  | Current forms appear to be difficult to understand; need review and updating. | Sent forms to a WR 227 class to see what they can do with it. No change since last update. | AM 1/14/15
Mandatory | Credit for prior learning reporting | Current | Courtney |  |  | IE |  | ü | ü | ü |  | Need to review how CPL credits are entered into Banner so that accurate reporting to CCWD is possible. | Pilot project at state level… waiting to see how that goes. Sharon - get update from C. | CF 4/28/14
Adv/Bonus | Prospective Student Recruitment and Communication Plan | Current | Courtney, Sharon |  |  | CR | ü | ü | ü | ü |  | Student Services communication to Prospective students is not coordinated between departments. Need to review what, when and how information is sent to students and revise as needed. | Working on A&R related materials per AACRAO recommendations. | SB 1/14/15
Sanity | Concerns Process , Title IX, Sexual Harassment Policies | Current | Gordon |  | ü | HR |  | ü | ü | ü |  | Review and update the Student Concerns, Employee Concerns, Harassment, Title IX, and Nondiscrimination policies and processes. Work with HR and Instruction. Will include updates to web pages. For Student Concerns process, may include a communication plan and associated materials. | Second reading college affairs approved. Next step is communication plan and website updates and other rollout activities. | GP 1/14/15
Adv/Bonus | New student housing: policies, practices, operations | Current | Gordon |  |  |  |  | ü | ü | ü |  | Need to review and update all operational polices and practices for New Student Housing. Implement software system for online applications/operations. | Ongoing. Software project underway, policies and practices are being reviewed. | GP 1/14/15
Adv/Bonus | Student climate assessment | Current | Karen |  |  | Div Comm; IE | ü | ü | ü | ü |  | COCC currently administers a "campus climate assessment' for employees, but does not do so for students. | Survey is completed. Currently compiling results to present to the campus. | KR 1/15/15
Mandatory | Fin Aid: Course Eligibility | Current | Kevin | ü | ü |  | ü | ü | ü | ü |  | Federal financial aid regulations now require that institutions only pay financial aid for courses that are required for a degree. Develop institution-wide process to advise students regarding this policy and develop internal tracking and student communication mechanisms. Review Banner baseline functionality supporting this federal requirement. | Waiting on recommendations to be approved. Changes in landscape? | KM 1/14/15
Adv/Bonus | CRM Implementation | Current | Sharon | ü |  |  | ü | ü | ü | ü |  | A CRM allows an institution to automate prospective, current and alumni communication plans, including letters, emails, e-newsletters, texts and other forms of communications. Plans can be customized to small and large groups of students based on various characteristics (for example, you can rate prospective students as to their level of interest, majors, etc.; communication plans will be customized based on this information). All student communications are currently done via manual processes. | In Progress - RFP committee meeting. Hoping to have the RFP out by Feb. | SB 1/14/15
Adv/Bonus | Online transfer equivalency tool | Current | Sharon | ü |  |  |  | ü | ü | ü |  | Implement a online tool that provides students/advisors with the ability to see how other college transfer courses articulate to COCC courses. Tool relies on articulatoin data already maintained by Degree Evaluators in Banner. Currently in test mode. | Holding | SB 1/14/15
Adv/Bonus | First-Year Experience | Current | Shawna |  | ü | Tutoring, CAP, OMA | ü | ü | ü | ü |  | Identified as a campus student success priority, develop an implementation plan for COCC's FYE program. Consider early interventions and deadlines concepts into the FYE program. | Waiting for PAT and Presidental approval of recommendations. | SE 1/14/15
Sanity | Bobcat orientation structure and staffing | Current | Shawna |  |  |  | ü | ü | ü | ü |  | Develop organizational structure to support BCO, including developing campus leads, task list/timeline and documentation. | In Progress | SE 1/14/15
Adv/Bonus | Policies & Practices for Exploratory Students | Current | Vickery |  | ü |  | ü | ü | ü | ü |  | Review best practices and recommend policy or practice changes to support exploratory students in determining a major. | Tracy Dula working on this - no details to report. | VV 2/12/14
Adv/Bonus | Associate of Science Degrees | Current | Vickery |  | ü |  | ü | ü | ü | ü |  | Expand current AS degree options; recommendations include: medical imaging, natural resources, outdoor leadership | OL currently going through approval. Several other degrees going through approval. | VV 1/14/15
Adv/Bonus | CAP Center role with recruiting and retention | Current | Vickery |  |  |  | ü | ü | ü | ü |  | Internal to CAP Center. Handling requests to meet with prospective students. | Piloting some things. Currently meeting with prospective students, but very ad-hoc at this point. | VV 1/14/15
Sanity | Nursing Application process simplification | Future | Jason, Chris, SeanaB | ü |  |  | ü | ü | ü | ü |  | Review and redesign the Nursing Application process to simplify our highly customized and complex Nursing App process. Redesign will utilize the Banner application and hopefully base banner processes. | Phase I is complete. Phase II is incorporating DW data into Argos reporting - eliminate manual work to check students GT accounts for exceptions or other anomolies. | CM 1/14/15
Adv/Bonus | Summer conferences | Future | Gordon |  |  |  |  | ü | ü | ü |  | If new student housing is approved, review all existing policies and processes related student summer conferencing. Includes hiring a student housing/conference and marketing coordinator. | Per Gordon - Summer Conferencing is a go and hiring for the position is underway. Added to the GREEN section on 1/14/15 by SB. | GP 1/14/15
Adv/Bonus | Title III Grant | Future | Alicia |  |  | Grants | ü | ü | ü | ü |  | Pursue Title III grant in support of campus student success strategies and campus wide student support services' gaps.
Sanity | Articulation Agreements | Future | Alicia |  | ü | In Sync | [5 empty] | Develop policy and process for current and new articulation agreements; includes discussion as to whether or not resources should be devoted to this work. Note that discussions will happen via the In Sync work group.
Sanity | Prerequisites | Future | Chris |  | ü |  |  | ü | ü | ü |  | Review how prerequisites are enforced via Banner; includes review of course set up process and baseline Banner functionality.
Sanity | Administrative withdrawal | Future | Chris, Jason | ? | ? |  |  | ü | ü | ü |  | Current admin withdrawal process requires that staff manually review a roster for every COCC course and manually drop students for non-attendance. Research and recommend options for an electronic process. | Waiting for MIS to implement Banner 9 Attendance module. Per 8/8/13 meeting - put back on Future list while we wait for MIS to implement Banner 9 Attendance. | Per Chris 5/22/13
Mandatory | Student ID look-up & FERPA | Future | Courtney | ü |  |  |  | ü | ü | ü | ü | Review federal regulations regarding assigning a student ID number and how a student may access their account; adjust policy and practices as needed. | Waiting for time/opportunity to start work. | Courtney 8/8/13
Mandatory | Student records retention policy | Future | Courtney |  |  |  |  | ü | ü | ü | ü | Review and adjust COCC’s student records retention policy and practices. Present to College Affairs for institutional adoption.
Adv/Bonus | Bachelor's Degree & WR121 waiver | Future | Courtney |  |  | AA |  | ü | ü | ü |  | Current practice is to waive WR 121 for any student with a bachelor’s degree; policy has never been approved. Bring to AA for consideration.
Adv/Bonus | Admissions & Records phone tree | Future | Seana B |  |  | IT |  | ü | ü | ü |  | Explore phone tree options with IT to better streamline heavy phone traffic in A&R.
Adv/Bonus | Reverse Transfer | Future | Courtney | ü |  |  | ü | ü | ü | ü |  | Review options for implementing a reverse transfer degree program with primary university partners, working with LBCC to adopt their policies, processes and programming (if appropriate) to support this initiative.
Sanity | Summer term policies and processes | Future | Courtney, Vickery | ü | ü |  | ü | ü | ü | ü |  | Unlike other terms, summer term does not that CDS students participate in advising; if a student is new for summer, they register in May and they are considered new for fall, and register with new students in July. Both of these issues are confusing for students. Should these policies and practices be adjusted? | Outcome of the re-admit process review: Create a new project called "Registration Groups and Summer Term issues". | SB 8/8/13
Adv/Bonus | GradTracks Planner | Future | Sharon | ü | ü |  | ü | ü | ü | ü |  | Initiate GT upgrade to allow implementation of “planner” functionality. Planner will allow students/advisors to document long-term course plans. Planner automatically shows how courses apply to cert/degree requirements and enables better forecasting of needed courses. | Upgrade to DW4.1.1 completed - wrapping up documentation | SB 8/1/2013
Adv/Bonus | Current Student Communication Plan | Future | Sharon |  |  | CR | ü | ü | ü | ü |  | Student Services communication to current students is not coordinated between departments. Need to review what, when and how information is sent to current students and revise as needed.
Adv/Bonus | SARS and NSA appointments | Future | Sharon | ü |  |  |  | ü | ü | ü |  | Current online appointment system enabled for placement testing; expand to allow new students to make online appointments for new student advising days.
Adv/Bonus | Promotion of student email | Future | Sharon |  |  | CR |  | ü | ü | ü |  | Determine current student email usage and ways to promote more ready use. | Updated Student Email login page on March 22, 2014. Hoping to streamline access for new students finding their email address/password. | SB 5/2/2014
Adv/Bonus | Academic Warning (intervention) | Future | Shawna |  | ü |  | ü | ü | ü | ü |  | Review current academic warning interventions, best practices and determine if changes are needed to COCC practices.
Adv/Bonus | Advising structure & systems | Future | Vickery |  | ü | FYE |  | ü | ü | ü |  | In light of recent data, review current advising structure, policies and processes to determine effectiveness; may be part of FYE discussions.
Sanity | Placement testing policy | Complete | Alicia |  | ü |  |  | ü | ü | ü |  | COCC administers approximately 4,500 on campus placement tests each year and another 1,000 to various community organizations (including high schools). Review current policy and determine recommended directions for dual credit courses and testing requests by high school testing requests and other community organizations. | Vickery & Courtney working on remaining process questions. Anticipate 1-2 hrs remaining on the project. | Per Alicia 5/22/13
Sanity | Course set up | Complete | Chris | ü | ü |  |  | ü | ü | ü | ü | Review baseline Banner functionality and redesign catalog- and course-level set up process; includes standard and specialty (umbrella, cohort, learning communities, instructor permission) courses. Standardized process.
Sanity | Academic warning (Banner/functionality) | Complete | Chris, Courtney |  |  |  |  | ü | ü | ü |  | Current report listing which students are on academic warning are inaccurate and as such, students are not properly notified of their status and registration requirements. Research baseline Banner and potential policy impacts. | Process is defined. Need to update student accounts and train staff on new process going forward. Plan to fully implement Fall 2013. Almost done - as of 8/8/13 SB | SB 8/8/13
Adv/Bonus | Graduating While not Enrolled | Complete | Courtney |  |  | AA |  | ü | ü | ü |  | Current policy is complicated and problematic; review and recommend changes.
Sanity | Admissions app & valid terms | Complete | Courtney | ü |  |  |  | ü | ü | ü |  | Current policy allows students to take a three term leave without having to reapply. Process is not automated and current student status is automatically voided after one term. | Make sure we sync up with Email account notification & creation process
Mandatory | Sexual Misconduct Policy | Complete | Gordon |  |  |  |  | ü | ü | ü | ü | Title IX requires that each institution have a sexual misconduct policy. Need to finalize current draft. | Completed first reading at college affairs. Almost completed. | SB 8/8/13
Sanity | Re-admit process/Reg Groups | Complete | Jason |  |  |  |  | ü | ü | ü |  | Current process to re-admit a student requires customization to Banner. Research indicates that this customization is negatively impacting other Banner processes (annual admissions requirement, academic warning reports). | Outcome of the re-admit process review: Create a new project called "Registration Groups and Summer Term issues". | Per group discussion 8/8/13 meeting
Adv/Bonus | Diversity in Hiring Practices Workshop | Complete | Karen |  |  | HR |  | ü | ü | ü | ü
Mandatory | Exec Order: Veterans' Support | Complete | Kevin |  |  |  |  | ü | ü | ü |  | Develop processes to support new federal regulations regarding services for Veterans, VA benefit reporting requirement and new TA regulations. |  | SB 5/22/13
Mandatory | DOD MOU: Veterans' Support | Complete | Kevin |  |  |  |  | ü | ü | ü |  | Develop processes to support new federal regulations regarding services for Veterans, VA benefit reporting requirement and new TA regulations. |  | SB 5/22/13
Mandatory | Awarding Credit by Test | Complete | Kevin |  |  |  |  | ü | ü | ü
Sanity | Transfer repeat course process | Complete | Sharon |  |  |  |  | ü | ü | ü
Sanity | Website: Calendar feature | Complete | Sharon |  |  |  |  | ü | ü | ü | ü
Adv/Bonus | SARS and assigned advisor appts | Complete | Sharon |  |  |  |  | ü | ü | ü |  | Current online appointment system enabled for placement testing; expand to allow CAP Center advisees to make appointment with CAP advisor online. |  | SB 5/22/13
Adv/Bonus | Early Alert Initiative | Complete | Shawna | ü | ü |  |  | ü | ü | ü |  |  | Removed from list due to other student success priorities as determined by campus wide process. | SB 8/20/13
Adv/Bonus | Success from the Start | Current | Shawna | ü |  | CR & Campus | ü | ü | ü | ü |  | Revise the enrollment process under the umbrella of “Success from the Start”; communicate all steps as part of getting started process and consider which aspects should be mandatory. Includes enrollment Getting Started checklist, and corresponding web page, staff training, reporting, and rollout plan. | Done - | SE 1/14/15
Mandatory | eRefund vendor change | Current | Seana B | ü |  | Fiscal |  | ü | ü | ü | ü | Sallie Mae sold their eRefund and Payment processing divisions to Higher One. We need to implement a solution with a new vendor for eRefund no later than March 2014. Payment processing will need to be converted/updated about a year after that. | Done! | CM 4/28/14
Mandatory | ePayment vendor change | Current | Seana B | ü |  | Fiscal |  | ü | ü | ü | ü | Contract with Sallie Mae/Higher one ends September 2014; will need to issue new RFP or consider using US Bank per eRefund RFP. | Done! | CM 2/12/14
Adv/Bonus | Diversity Education Award Program | Current | Karen |  |  |  |  | ü | ü | ü | ü | Working with Diversity Committee, develop a process for recognizing staff and students who participate in 15 hours of diversity training/education. | Project is completed. - check with Karen | KR 1/15/15
Adv/Bonus | Academic coaching/mentoring | Removed | Shawna |  | ü |  |  | ü | ü | ü |  | Removed from list due to other student success priorities as determined by campus wide process. |  | SB 8/20/13
Adv/Bonus | Certificate & Degree Exceptions/Waivers | Removed | Courtney | ? |  | AA |  | ü | ü | ü |  | Merged with auto awarding certificates and degrees initiative
Sanity | Fin Aid & GradTracks | Removed | Jason |  |  |  |  | ü | ü | ü |  | Using with max credit; working with transcript/degree evaluators for other needs
Adv/Bonus | Early Interventions & Deadlines | Current | Shawna |  | ü |  | ü | ü | ü | ü |  | Identified as a campus student success priority, develop an implementation plan for early interventions and early enrollment deadlines. | Folded into FYE